## Overview
EcoLoop execution harness
As of 15 October 2026 · Collaborative planning · No application implementation claimed
Update Tasks inputs; phase progress counts leaf units and gates once.
Phase | Outcome | Horizon | Units | Verified | Progress | In progress | Dependency open | Phase gate
P00 | Planning and scope approval | Planning | 13 | 0 | 0% | 0 | 10 | Dependency open
P01 | Trusted foundation and contracts | Demo | 13 | 0 | 0% | 0 | 13 | Dependency open
P02 | Deterministic baseline and synthetic household flow | Demo | 13 | 0 | 0% | 0 | 13 | Dependency open
P03 | Gemini intake and single-orchestrator household journey | Demo | 13 | 0 | 0% | 0 | 13 | Dependency open
P04 | Google deployment and submission readiness | Demo | 13 | 0 | 0% | 0 | 13 | Dependency open
P05 | Institutional kitchen extension | Expansion | 13 | 0 | 0% | 0 | 13 | Dependency open
P06 | Qualified recovery coordination | Expansion | 13 | 0 | 0% | 0 | 13 | Dependency open
P07 | Organics and processor evidence | Expansion | 13 | 0 | 0% | 0 | 13 | Dependency open
P08 | Permissioned pilot and operating model | Pilot | 13 | 0 | 0% | 0 | 13 | Dependency open
P09 | Repair reuse and material exchange discovery | Expansion | 13 | 0 | 0% | 0 | 13 | Dependency open
P10 | Energy and water modules discovery | Expansion | 13 | 0 | 0% | 0 | 13 | Dependency open
P11 | Ecosystem scale and commercial reliability | Scale | 13 | 0 | 0% | 0 | 13 | Dependency open
Total planned units | 156
Verified units | 0
Demo gate | Dependency open
Blueprint folder | https://drive.google.com/drive/folders/1mhYQLzTWc1uwqF9BkkkIy44y7R6GikpC
Control room link | Added after document publication
Formula verification cannot establish that evidence is truthful; accountable review remains required.

## Tasks
EcoLoop tasks — live completion and evidence
Use filters; preserve row order. Checked boxes need evidence, reviewer, date and verified prerequisites.
Initial state: proposed tasks only. Owner roles are placeholders; coding is not authorized by this documentation request.
Unit ID | Phase | Parent task | Granular unit | Owner | Status | Done | Calculated result | Evidence link | Reviewer | Updated (ISO) | Prerequisite 1 | Prerequisite 2 | Prerequisite 3 | Dependency readiness | Acceptance condition | Expected evidence | Estimate hours | Context tokens | Requirement / journey | Blocker / notes | Horizon
P00.01.01 | P00 | P00.01 Product and evidence | Review source inventory and conflicts | Product owner | Not started | FALSE | Open | [6 empty] | Ready | Coverage and contradiction register acknowledged; source gaps have owners | Research inventory + product source review |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.01.02 | P00 | P00.01 Product and evidence | Select initial actor and decision window | Product owner | Not started | FALSE | Dependency open |  |  |  | P00.01.01 |  |  | Dependency open | Named cook/buyer, authority and before-cooking trigger documented | Product strategy scope decision |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.01.03 | P00 | P00.01 Product and evidence | Approve one-lane demo boundary | Product owner | Not started | FALSE | Dependency open |  |  |  | P00.01.02 |  |  | Dependency open | Household path chosen or alternative documented; other lanes staged | Signed scope decision DEC-PLAT-001 |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.01.04 | P00 | P00.01 Product and evidence | Define success and stop conditions | Product owner | Not started | FALSE | Dependency open |  |  |  | P00.01.03 |  |  | Dependency open | Decision correctness, effort and zero unsafe actions defined before trial | Pilot/benchmark acceptance record |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.02.01 | P00 | P00.02 Constraints and access | Verify contest eligibility and deadline | Technical lead | Not started | FALSE | Open | [6 empty] | Ready | Official terms, roster status and exact cutoff uncertainty recorded | Official source URLs and eligibility note |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.02.02 | P00 | P00.02 Constraints and access | Inventory cloud and model access | Technical lead | Not started | FALSE | Dependency open |  |  |  | P00.02.01 |  |  | Dependency open | IAM, billing, region, quota and supported runtime verified without exposing secrets | Redacted access checklist |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.02.03 | P00 | P00.02 Constraints and access | Review food policy and measurement assumptions | Technical lead | Not started | FALSE | Dependency open |  |  |  | P00.02.02 |  |  | Dependency open | Unsupported universal thresholds/cutoffs rejected; reviewer named | Policy discrepancy register |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.02.04 | P00 | P00.02 Constraints and access | Approve privacy and partner boundaries | Technical lead | Not started | FALSE | Dependency open |  |  |  | P00.02.03 |  |  | Dependency open | Consent, public-repo data exclusion and simulated-only adapters specified | Privacy/partner decision record |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.03.01 | P00 | P00.03 Execution setup | Review HLD and LLD against scope | Technical lead | Not started | FALSE | Open | [6 empty] | Ready | Auth, versions, approvals, idempotency and failure contracts agreed | Technical design review |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.03.02 | P00 | P00.03 Execution setup | Assign owners and estimates | Technical lead | Not started | FALSE | Dependency open |  |  |  | P00.03.01 |  |  | Dependency open | Named owner, reviewer and effort for first executable work packet | Updated tracker rows |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.03.03 | P00 | P00.03 Execution setup | Exercise harness status and recovery | Technical lead | Not started | FALSE | Dependency open |  |  |  | P00.03.02 |  |  | Dependency open | Checkbox alone cannot verify; dependencies and evidence gates recalculate | Harness verification record |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.03.04 | P00 | P00.03 Execution setup | Authorize implementation phase | Technical lead | Not started | FALSE | Dependency open |  |  |  | P00.03.03 |  |  | Dependency open | Human authorizes coding scope; document-only restriction explicitly lifted | Authorization record |  | 6000 | REQ-SCOPE-01 | Proposed work; implementation not authorized by this documentation request. | Planning
P00.90.01 | P00 | P00.90 Phase gate | Review and accept planning and scope approval | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P00.01.04 | P00.02.04 | P00.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P00-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Planning
P01.01.01 | P01 | P01.01 Identity and permissions | Define membership and permission matrix | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P00.90.01 |  |  | Dependency open | Each protected operation maps actor, tenant and permission | Auth contract REQ-AUTH-01 |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.01.02 | P01 | P01.01 Identity and permissions | Implement verified identity boundary | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P01.01.01 |  |  | Dependency open | Missing/invalid token rejected; tenant never defaults | Auth check evidence |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.01.03 | P01 | P01.01 Identity and permissions | Implement current membership and revocation checks | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P01.01.02 |  |  | Dependency open | Revoked membership fails even with a still-valid token | Revocation and wrong-tenant evidence |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.01.04 | P01 | P01.01 Identity and permissions | Prove denial across roles and tenants | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P01.01.03 |  |  | Dependency open | Read/write isolation and guessed IDs tested | Negative authorization matrix |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.02.01 | P01 | P01.02 Canonical records | Define typed records and units | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P00.90.01 |  |  | Dependency open | Candidate, fact, proposal, evidence, outcome schemas include version and provenance | Schema review |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.02.02 | P01 | P01.02 Canonical records | Define tenant paths and server-only writes | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P01.02.01 |  |  | Dependency open | No global list or browser mutation bypass; server IAM assessed | Firestore access design |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.02.03 | P01 | P01.02 Canonical records | Implement atomic versioned confirmation | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P01.02.02 |  |  | Dependency open | Stale version causes conflict; repeat submission does not duplicate facts | Confirmation conflict evidence |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.02.04 | P01 | P01.02 Canonical records | Prove durable audit and restart behavior | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P01.02.03 |  |  | Dependency open | Business state survives restart; sensitive content excluded from logs | Persistence and redaction evidence |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.03.01 | P01 | P01.03 Runtime foundation | Confirm supported frontend and Node pairing | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P00.90.01 |  |  | Dependency open | App Hosting compatibility verified for actual pinned versions | Runtime matrix |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.03.02 | P01 | P01.03 Runtime foundation | Configure authenticated API client and origins | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P01.03.01 |  |  | Dependency open | Environment URL used; production origins explicit; localhost not shipped | Client/CORS evidence |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.03.03 | P01 | P01.03 Runtime foundation | Create health and deployment contract | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P01.03.02 |  |  | Dependency open | Root health path stable; PORT and startup behavior documented | Health/deployment smoke evidence |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.03.04 | P01 | P01.03 Runtime foundation | Set budgets and model call caps | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P01.03.03 |  |  | Dependency open | Quota, maximum attempts/tokens and alerts have owners | Budget configuration evidence |  | 6000 | REQ-AUTH-01 / REQ-FACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P01.90.01 | P01 | P01.90 Phase gate | Review and accept trusted foundation and contracts | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P01.01.04 | P01.02.04 | P01.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P01-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Demo
P02.01.01 | P02 | P02.01 Decision rules | Specify pantry and meal change fixtures | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P01.90.01 |  |  | Dependency open | Stock freshness, ownership, units and consumed quantities explicit | Fixture definitions |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.01.02 | P02 | P02.01 Decision rules | Implement unit-safe quantity reconciliation | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P02.01.01 |  |  | Dependency open | No g/ml conversion without verified factor; no negative stock | Boundary-case outputs |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.01.03 | P02 | P02.01 Decision rules | Implement portion and cutoff rules | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P02.01.02 |  |  | Dependency open | Zero diners and after-cutoff behavior deterministic and explained | Rule-case outputs |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.01.04 | P02 | P02.01 Decision rules | Implement immutable simulated proposal | Backend engineer | Not started | FALSE | Dependency open |  |  |  | P02.01.03 |  |  | Dependency open | Snapshot versions, expiry and preview hash stored; simulated true | Proposal contract evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.02.01 | P02 | P02.02 Evaluation baseline | Annotate household gold cases | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P01.90.01 |  |  | Dependency open | Labels and rejection reasons independently reviewed | Gold-case register |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.02.02 | P02 | P02.02 Evaluation baseline | Run rules-only baseline | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P02.02.01 |  |  | Dependency open | Fixed input fixtures and privileges; raw results retained | Baseline run ID |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.02.03 | P02 | P02.02 Evaluation baseline | Add adversarial and concurrency assertions | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P02.02.02 |  |  | Dependency open | Injected text, stale facts and approval races covered | Negative-case results |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.02.04 | P02 | P02.02 Evaluation baseline | Define fair comparison protocol | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P02.02.03 |  |  | Dependency open | Equivalent inputs, model budget and reporting denominator frozen | Evaluation protocol |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.03.01 | P02 | P02.03 Human workflow | Build synthetic scenario start and actor view | Frontend engineer | Not started | FALSE | Dependency open |  |  |  | P01.90.01 |  |  | Dependency open | Demo tenant and simulated records conspicuous | Scenario screen evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.03.02 | P02 | P02.03 Human workflow | Build candidate/fact review interaction | Frontend engineer | Not started | FALSE | Dependency open |  |  |  | P02.03.01 |  |  | Dependency open | Field changes explicit; confirm distinct from extraction | Review-flow evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.03.03 | P02 | P02.03 Human workflow | Build proposal preview and approval interaction | Frontend engineer | Not started | FALSE | Dependency open |  |  |  | P02.03.02 |  |  | Dependency open | Actor sees quantities, uncertainty, expiry and simulation before approving | Approval UX evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.03.04 | P02 | P02.03 Human workflow | Build honest outcome journal states | Frontend engineer | Not started | FALSE | Dependency open |  |  |  | P02.03.03 |  |  | Dependency open | Measured, simulated and unknown separated; loading/empty/error/retry shown | Outcome state screenshots |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P02.90.01 | P02 | P02.90 Phase gate | Review and accept deterministic baseline and synthetic household flow | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P02.01.04 | P02.02.04 | P02.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P02-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Demo
P03.01.01 | P03 | P03.01 Structured intake | Verify allowed Vertex model and extraction schema | AI engineer | Not started | FALSE | Dependency open |  |  |  | P02.90.01 |  |  | Dependency open | Actual model ID/region recorded; parse output constrained | Model access and schema evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.01.02 | P03 | P03.01 Structured intake | Implement text intake and optional image upload | AI engineer | Not started | FALSE | Dependency open |  |  |  | P03.01.01 |  |  | Dependency open | Content type/size/consent validated; optional modality can be cut | Upload/input evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.01.03 | P03 | P03.01 Structured intake | Enforce candidate isolation and uncertainty | AI engineer | Not started | FALSE | Dependency open |  |  |  | P03.01.02 |  |  | Dependency open | AI output never writes canonical facts; missing values remain unknown | Isolation evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.01.04 | P03 | P03.01 Structured intake | Verify injection and malformed-output fallback | AI engineer | Not started | FALSE | Dependency open |  |  |  | P03.01.03 |  |  | Dependency open | Receipt instructions ignored; bounded retry then human correction | Extraction adversarial results |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.02.01 | P03 | P03.02 Agent orchestration | Define minimal allowlisted tool contracts | AI engineer | Not started | FALSE | Dependency open |  |  |  | P02.90.01 |  |  | Dependency open | Tools receive scoped resource IDs and checked permissions | Tool registry review |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.02.02 | P03 | P03.02 Agent orchestration | Implement bounded orchestrator run | AI engineer | Not started | FALSE | Dependency open |  |  |  | P03.02.01 |  |  | Dependency open | Maximum turns/cost/deadline; no self-authorized execution | Trace with termination evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.02.03 | P03 | P03.02 Agent orchestration | Bind approval to versioned proposal | AI engineer | Not started | FALSE | Dependency open |  |  |  | P03.02.02 |  |  | Dependency open | Expiry, current membership, hash and facts rechecked on approval | Stale/revoked approval evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.02.04 | P03 | P03.02 Agent orchestration | Make approval retries idempotent | AI engineer | Not started | FALSE | Dependency open |  |  |  | P03.02.03 |  |  | Dependency open | Duplicate concurrent request yields one simulated execution | Concurrency run evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.03.01 | P03 | P03.03 Golden flow integration | Connect text to review to changed meal | Fullstack engineer | Not started | FALSE | Dependency open |  |  |  | P02.90.01 |  |  | Dependency open | Real Gemini response goes through explicit human confirmation | J-H01 trace |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.03.02 | P03 | P03.03 Golden flow integration | Connect proposal to mock action to evidence | Fullstack engineer | Not started | FALSE | Dependency open |  |  |  | P03.03.01 |  |  | Dependency open | No real checkout or dispatch; visible simulated outcome | J-H01 full-flow recording |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.03.03 | P03 | P03.03 Golden flow integration | Handle connectivity and cancellation | Fullstack engineer | Not started | FALSE | Dependency open |  |  |  | P03.03.02 |  |  | Dependency open | Resume from persisted state; ambiguous action state reconciled | Recovery-flow evidence |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.03.04 | P03 | P03.03 Golden flow integration | Compare against rules and plain Gemini | Fullstack engineer | Not started | FALSE | Dependency open |  |  |  | P03.03.03 |  |  | Dependency open | Correctness/unsafe actions/latency/effort reported with run IDs | Paired benchmark results |  | 6000 | J-H01 / REQ-ACT-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P03.90.01 | P03 | P03.90 Phase gate | Review and accept gemini intake and single-orchestrator household journey | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P03.01.04 | P03.02.04 | P03.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P03-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Demo
P04.01.01 | P04 | P04.01 Deploy core | Prepare App Hosting and Cloud Run manifests | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P03.90.01 |  |  | Dependency open | Pinned runtime, secrets references and service identities reviewed | Deployment config review |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.01.02 | P04 | P04.01 Deploy core | Deploy isolated demo environment | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P04.01.01 |  |  | Dependency open | Public app URL and secured backend reachable; no real private data | Deployment URLs and revision IDs |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.01.03 | P04 | P04.01 Deploy core | Verify cross-service authentication and health | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P04.01.02 |  |  | Dependency open | Anonymous mutation and foreign tenant access fail on deployed system | Deployed negative checks |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.01.04 | P04 | P04.01 Deploy core | Prove rollback and degraded mode | Platform engineer | Not started | FALSE | Dependency open |  |  |  | P04.01.03 |  |  | Dependency open | Prior revision recoverable; model outage visibly handled | Rollback/degraded evidence |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.02.01 | P04 | P04.02 Release checks | Verify end-to-end mobile flow | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P03.90.01 |  |  | Dependency open | 360px flow, keyboard focus, labels, 44px targets and all states reviewed | Browser evidence |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.02.02 | P04 | P04.02 Release checks | Record actual performance and cost | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P04.02.01 |  |  | Dependency open | P50/P95, model tokens, errors and cold-start caveat measured | Run-specific metrics |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.02.03 | P04 | P04.02 Release checks | Audit public repo and demo claims | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P04.02.02 |  |  | Dependency open | Secrets, real data, unsupported impact and third-party rights reviewed | Release review record |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.02.04 | P04 | P04.02 Release checks | Review all critical failures | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P04.02.03 |  |  | Dependency open | No unowned critical auth/safety/data-loss failure accepted | Critical issue disposition |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.03.01 | P04 | P04.03 Submission assets | Prepare final proposal document and deck content | Product owner | Not started | FALSE | Dependency open |  |  |  | P03.90.01 |  |  | Dependency open | Problem, Google AI role, evidence and limitations align with working demo | Proposal/PDF artifact |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.03.02 | P04 | P04.03 Submission assets | Record strictly under-three-minute demo | Product owner | Not started | FALSE | Dependency open |  |  |  | P04.03.01 |  |  | Dependency open | Public access checked; live behavior and simulations identified | Final video link/duration |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.03.03 | P04 | P04.03 Submission assets | Validate submission packet and eligibility | Product owner | Not started | FALSE | Dependency open |  |  |  | P04.03.02 |  |  | Dependency open | Repository, URL, deck, video, track and roster checked against live terms | Submission checklist |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.03.04 | P04 | P04.03 Submission assets | Submit and retain receipt | Product owner | Not started | FALSE | Dependency open |  |  |  | P04.03.03 |  |  | Dependency open | Authorized human submits before confirmed cutoff; receipt retained | Submission confirmation |  | 6000 | REQ-DEPLOY-01 | Proposed work; implementation not authorized by this documentation request. | Demo
P04.90.01 | P04 | P04.90 Phase gate | Review and accept google deployment and submission readiness | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P04.01.04 | P04.02.04 | P04.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P04-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Demo
P05.01.01 | P05 | P05.01 Roster and preparation authority | Map kitchen roles and source authority | Product/backend team | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Headcount reporter cannot override chef/menu policy | J-K01 role map |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.01.02 | P05 | P05.01 Roster and preparation authority | Model per-batch last reversible point | Product/backend team | Not started | FALSE | Dependency open |  |  |  | P05.01.01 |  |  | Dependency open | Chef-specified timestamp/timezone/version; no universal 45-minute rule | Batch/cutoff contract |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.01.03 | P05 | P05.01 Roster and preparation authority | Capture and confirm attendance exceptions | Product/backend team | Not started | FALSE | Dependency open |  |  |  | P05.01.02 |  |  | Dependency open | Changes record source, effective date and approved diners | Roster change evidence |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.01.04 | P05 | P05.01 Roster and preparation authority | Reject late and conflicting adjustments | Product/backend team | Not started | FALSE | Dependency open |  |  |  | P05.01.03 |  |  | Dependency open | Already-started/closed batch yields hold or new human decision | Cutoff/concurrency cases |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.02.01 | P05 | P05.02 Chef and measurements | Review dietary and nutrition constraints | Kitchen partner lead | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Qualified operator owns approved menu and substitutions | Operator-reviewed policy |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.02.02 | P05 | P05.02 Chef and measurements | Implement chef approval of batch changes | Kitchen partner lead | Not started | FALSE | Dependency open |  |  |  | P05.02.01 |  |  | Dependency open | Arithmetic deterministic; prep change requires authorized chef | Chef approval trace |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.02.03 | P05 | P05.02 Chef and measurements | Separate preparation unserved and plate weights | Kitchen partner lead | Not started | FALSE | Dependency open |  |  |  | P05.02.02 |  |  | Dependency open | Scale/time/tare/category metadata recorded distinctly | Stage measurement records |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.02.04 | P05 | P05.02 Chef and measurements | Reconcile planned versus actual served meals | Kitchen partner lead | Not started | FALSE | Dependency open |  |  |  | P05.02.03 |  |  | Dependency open | Denominator actual served; unknown data not inferred | Kitchen outcome calculation |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.03.01 | P05 | P05.03 Kitchen validation | Annotate K-lane failure cases | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Late event, diet mismatch, role escalation and double count covered | K gold cases |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.03.02 | P05 | P05.03 Kitchen validation | Compare against simple headcount and batch rules | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P05.03.01 |  |  | Dependency open | Equivalent roster and cutoff inputs used across arms | K comparative run |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.03.03 | P05 | P05.03 Kitchen validation | Pilot with authorized kitchen | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P05.03.02 |  |  | Dependency open | Site consent, workload and food-service oversight recorded | Pilot protocol and permission |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.03.04 | P05 | P05.03 Kitchen validation | Choose continue revise or stop | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P05.03.03 |  |  | Dependency open | Observed effort/correctness supports explicit decision | Kitchen gate report |  | 6000 | J-K01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P05.90.01 | P05 | P05.90 Phase gate | Review and accept institutional kitchen extension | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P05.01.04 | P05.02.04 | P05.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P05-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Expansion
P06.01.01 | P06 | P06.01 Policy and donor eligibility | Obtain qualified policy review | Safety/partner lead | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Jurisdiction, category, source version and effective dates recorded | Policy sign-off |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.01.02 | P06 | P06.01 Policy and donor eligibility | Implement donor evidence completeness | Safety/partner lead | Not started | FALSE | Dependency open |  |  |  | P06.01.01 |  |  | Dependency open | Unused/unserved status, custody and required handling records explicit | FoodOffer schema/evidence |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.01.03 | P06 | P06.01 Policy and donor eligibility | Block excluded or unreviewed offers | Safety/partner lead | Not started | FALSE | Dependency open |  |  |  | P06.01.02 |  |  | Dependency open | Plate/spoiled food rejected; unknown state held for review | R negative cases |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.01.04 | P06 | P06.01 Policy and donor eligibility | Require human eligibility decision | Safety/partner lead | Not started | FALSE | Dependency open |  |  |  | P06.01.03 |  |  | Dependency open | Reviewer identity and policy version persisted; AI cannot certify | Qualified review record |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.02.01 | P06 | P06.02 Capacity and agreements | Verify NGO and recipient organizations | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Permissions, handling capability and contact consent documented | Partner onboarding evidence |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.02.02 | P06 | P06.02 Capacity and agreements | Record separate NGO and recipient acceptance | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P06.02.01 |  |  | Dependency open | Capacity, diet, window and transport confirmed independently | Acceptance records |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.02.03 | P06 | P06.02 Capacity and agreements | Create scoped cross-tenant offer projection | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P06.02.02 |  |  | Dependency open | Only approved fields shared; no donor inventory disclosure | Sharing security review |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.02.04 | P06 | P06.02 Capacity and agreements | Reserve capacity and revalidate at approval | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P06.02.03 |  |  | Dependency open | Expiry, cancellation and concurrent claims prevent double dispatch | Reservation race evidence |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.03.01 | P06 | P06.03 Custody and exception handling | Record pickup delivery and accepted mass | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Signed actor/time/evidence at each custody change | Custody ledger |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.03.02 | P06 | P06.03 Custody and exception handling | Handle partial rejection and failed delivery | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P06.03.01 |  |  | Dependency open | No automatic reroute; accountable human chooses permitted disposition | Exception walkthrough |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.03.03 | P06 | P06.03 Custody and exception handling | Implement withdrawal and incident escalation | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P06.03.02 |  |  | Dependency open | Revoked offers cannot dispatch; incidents linked to affected batches | Recall/escalation evidence |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.03.04 | P06 | P06.03 Custody and exception handling | Run simulation before any live pilot | Partner operations lead | Not started | FALSE | Dependency open |  |  |  | P06.03.03 |  |  | Dependency open | R-lane red-team cases pass and physical partner authorization explicit | Recovery pilot readiness report |  | 6000 | J-R01 / REQ-POL-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P06.90.01 | P06 | P06.90 Phase gate | Review and accept qualified recovery coordination | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P06.01.04 | P06.02.04 | P06.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P06-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Expansion
P07.01.01 | P07 | P07.01 Accepted loads | Verify local operator and accepted-material rules | Processor partner lead | Not started | FALSE | Dependency open |  |  |  | P06.90.01 |  |  | Dependency open | Operator authorization and exclusions documented per site | Operator/policy record |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.01.02 | P07 | P07.01 Accepted loads | Capture segregated source load | Processor partner lead | Not started | FALSE | Dependency open |  |  |  | P07.01.01 |  |  | Dependency open | Origin, category, quantity and contaminated fraction explicit | J-O01 load record |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.01.03 | P07 | P07.01 Accepted loads | Record calibrated gross tare and net weights | Processor partner lead | Not started | FALSE | Dependency open |  |  |  | P07.01.02 |  |  | Dependency open | Units, scale, timestamp and operator attestation preserved | Weigh ticket |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.01.04 | P07 | P07.01 Accepted loads | Reject contaminated or unauthorized collection | Processor partner lead | Not started | FALSE | Dependency open |  |  |  | P07.01.03 |  |  | Dependency open | No assumed composting route for every organic material | Load rejection evidence |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.02.01 | P07 | P07.02 Processing chain | Record collected accepted rejected and processed stages | Backend/operations team | Not started | FALSE | Dependency open |  |  |  | P06.90.01 |  |  | Dependency open | Each stage separate; pickup never treated as processing | Stage ledger |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.02.02 | P07 | P07.02 Processing chain | Support partial acceptance and transfer reconciliation | Backend/operations team | Not started | FALSE | Dependency open |  |  |  | P07.02.01 |  |  | Dependency open | No duplicate mass across operator and collector views | Partial-load cases |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.02.03 | P07 | P07.02 Processing chain | Record process outputs moisture and unresolved residual | Backend/operations team | Not started | FALSE | Dependency open |  |  |  | P07.02.02 |  |  | Dependency open | Boundary/time basis explicit; no naive wet-to-dry equality | Mass-balance analysis |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.02.04 | P07 | P07.02 Processing chain | Attach auditable processor receipt | Backend/operations team | Not started | FALSE | Dependency open |  |  |  | P07.02.03 |  |  | Dependency open | Source/evidence identity and dispute state visible | Processing evidence |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.03.01 | P07 | P07.03 Circularity validation | Define counterfactual before diversion claims | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P06.90.01 |  |  | Dependency open | Destination alternatives and evidence requirements recorded | Measurement protocol |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.03.02 | P07 | P07.03 Circularity validation | Test receipt extraction against human entry | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P07.03.01 |  |  | Dependency open | AI benefit measured on multilingual/inconsistent documents | O-lane comparison |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.03.03 | P07 | P07.03 Circularity validation | Run authorized operator pilot | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P07.03.02 |  |  | Dependency open | Collection cost, reject rate and missing receipts measured | Pilot dataset |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.03.04 | P07 | P07.03 Circularity validation | Approve only substantiated reporting | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P07.03.03 |  |  | Dependency open | Collected/processed/estimated/unknown labels remain separate | Outcome claims review |  | 6000 | J-O01 / REQ-IMPACT-01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P07.90.01 | P07 | P07.90 Phase gate | Review and accept organics and processor evidence | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P07.01.04 | P07.02.04 | P07.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P07-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Expansion
P08.01.01 | P08 | P08.01 Pilot design | Recruit consenting decision owners | Research lead | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Voluntary participants; withdrawal and data use explained | Consent record |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.01.02 | P08 | P08.01 Pilot design | Collect baseline without retrospective invention | Research lead | Not started | FALSE | Dependency open |  |  |  | P08.01.01 |  |  | Dependency open | Physical measurements and effort logged with missingness | Baseline dataset |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.01.03 | P08 | P08.01 Pilot design | Run comparison with predeclared measures | Research lead | Not started | FALSE | Dependency open |  |  |  | P08.01.02 |  |  | Dependency open | Comparable periods/arms; seasonality and attrition recorded | Pilot protocol/results |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.01.04 | P08 | P08.01 Pilot design | Interview failures and non-users | Research lead | Not started | FALSE | Dependency open |  |  |  | P08.01.03 |  |  | Dependency open | Logistics, habit and input burden investigated | Interview synthesis |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.02.01 | P08 | P08.02 Economics and pricing | Measure support and model cost per completed decision | Product owner | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | Failed calls/retries/operator minutes included | Cost worksheet |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.02.02 | P08 | P08.02 Economics and pricing | Test payer and willingness-to-pay hypothesis | Product owner | Not started | FALSE | Dependency open |  |  |  | P08.02.01 |  |  | Dependency open | Buyer and beneficiary distinguished; no invented commitments | Pricing interview evidence |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.02.03 | P08 | P08.02 Economics and pricing | Calculate scenario unit economics | Product owner | Not started | FALSE | Dependency open |  |  |  | P08.02.02 |  |  | Dependency open | Compute/storage/support/verification/partner costs explicit | Sensitivity model |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.02.04 | P08 | P08.02 Economics and pricing | Decide viable segment and expansion budget | Product owner | Not started | FALSE | Dependency open |  |  |  | P08.02.03 |  |  | Dependency open | Evidence supports target segment or stop/pivot | Commercial decision |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.03.01 | P08 | P08.03 Operational trust | Assign incident and data-rights owners | Operations lead | Not started | FALSE | Dependency open |  |  |  | P04.90.01 |  |  | Dependency open | On-call routes, deletion exceptions and escalation time defined | Operations runbook |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.03.02 | P08 | P08.03 Operational trust | Validate retention revocation and deletion | Operations lead | Not started | FALSE | Dependency open |  |  |  | P08.03.01 |  |  | Dependency open | Derived records and media affected; audit legal hold scoped | Data lifecycle evidence |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.03.03 | P08 | P08.03 Operational trust | Review fairness and accessibility | Operations lead | Not started | FALSE | Dependency open |  |  |  | P08.03.02 |  |  | Dependency open | Low-connectivity/language constraints and exclusion harms assessed | Accessibility/equity findings |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.03.04 | P08 | P08.03 Operational trust | Publish measured pilot limits | Operations lead | Not started | FALSE | Dependency open |  |  |  | P08.03.03 |  |  | Dependency open | Claims preserve sample/time/geography and counterfactual uncertainty | Pilot report |  | 6000 | REQ-PILOT-01 | Proposed work; implementation not authorized by this documentation request. | Pilot
P08.90.01 | P08 | P08.90 Phase gate | Review and accept permissioned pilot and operating model | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P08.01.04 | P08.02.04 | P08.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P08-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Pilot
P09.01.01 | P09 | P09.01 Asset lifecycle | Choose a single repair or reuse category | Product/domain lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | Hazard, ownership and service capability fit recorded | J-U01 scope decision |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.01.02 | P09 | P09.01 Asset lifecycle | Model condition evidence and ownership rights | Product/domain lead | Not started | FALSE | Dependency open |  |  |  | P09.01.01 |  |  | Dependency open | Photo is evidence, not authenticity/safety certification | Asset contract |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.01.03 | P09 | P09.01 Asset lifecycle | Draft repair-first options and human choice | Product/domain lead | Not started | FALSE | Dependency open |  |  |  | P09.01.02 |  |  | Dependency open | AI summarizes issue; technician owns diagnosis | Repair journey review |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.01.04 | P09 | P09.01 Asset lifecycle | Capture completed repair or transfer outcome | Product/domain lead | Not started | FALSE | Dependency open |  |  |  | P09.01.03 |  |  | Dependency open | Acceptance and actual service evidence required | Outcome record |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.02.01 | P09 | P09.02 Service marketplace | Verify repair and reuse partners | Partner lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | Geography, accepted items, credentials and liability agreed | Partner records |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.02.02 | P09 | P09.02 Service marketplace | Define availability matching and explicit fees | Partner lead | Not started | FALSE | Dependency open |  |  |  | P09.02.01 |  |  | Dependency open | Availability consented; no unapproved purchase | Matching/quote contract |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.02.03 | P09 | P09.02 Service marketplace | Handle refusal dispute and return | Partner lead | Not started | FALSE | Dependency open |  |  |  | P09.02.02 |  |  | Dependency open | Custody, ownership and responsibility transitions explicit | Exception blueprint |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.02.04 | P09 | P09.02 Service marketplace | Protect private location and contact data | Partner lead | Not started | FALSE | Dependency open |  |  |  | P09.02.03 |  |  | Dependency open | Share minimum only after consent and match approval | Sharing audit |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.03.01 | P09 | P09.03 Module validation | Build category-specific rule and AI baselines | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | Same diagnosis evidence; no autonomous unsafe repair advice | U evaluation protocol |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.03.02 | P09 | P09.03 Module validation | Test identity fraud and prohibited material cases | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P09.03.01 |  |  | Dependency open | Unsafe/hazardous/ownership-unclear listings blocked | Negative cases |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.03.03 | P09 | P09.03 Module validation | Pilot with one authorized partner | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P09.03.02 |  |  | Dependency open | Repair success, time/cost and follow-through measured | Pilot results |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.03.04 | P09 | P09.03 Module validation | Gate broader materials exchange | Evaluation reviewer | Not started | FALSE | Dependency open |  |  |  | P09.03.03 |  |  | Dependency open | Repeat demand and viable trust costs demonstrated | Reuse expansion decision |  | 6000 | J-U01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P09.90.01 | P09 | P09.90 Phase gate | Review and accept repair reuse and material exchange discovery | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P09.01.04 | P09.02.04 | P09.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P09-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Expansion
P10.01.01 | P10 | P10.01 Energy decisions | Identify consenting site and actionable decision | Energy domain lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | Bill review or schedule advisory selected; no device control | J-E01 scope |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.01.02 | P10 | P10.01 Energy decisions | Verify meter bill and tariff data rights | Energy domain lead | Not started | FALSE | Dependency open |  |  |  | P10.01.01 |  |  | Dependency open | Units, periods, calibration and legitimate access documented | Energy data contract |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.01.03 | P10 | P10.01 Energy decisions | Build deterministic normalized baseline | Energy domain lead | Not started | FALSE | Dependency open |  |  |  | P10.01.02 |  |  | Dependency open | Weather/occupancy/period effects considered; uncertainty explicit | Baseline method |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.01.04 | P10 | P10.01 Energy decisions | Evaluate advisory with human authorization | Energy domain lead | Not started | FALSE | Dependency open |  |  |  | P10.01.03 |  |  | Dependency open | Measured kWh and comfort/service constraints retained | Energy validation results |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.02.01 | P10 | P10.02 Water decisions | Choose metered conservation or leak workflow | Water domain lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | Site authority, response operator and measurement boundary set | J-W01 scope |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.02.02 | P10 | P10.02 Water decisions | Validate volume time and sensor reliability | Water domain lead | Not started | FALSE | Dependency open |  |  |  | P10.02.01 |  |  | Dependency open | Missing/offline sensors shown; no invented meter readings | Water data contract |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.02.03 | P10 | P10.02 Water decisions | Design human-reviewed anomaly workflow | Water domain lead | Not started | FALSE | Dependency open |  |  |  | P10.02.02 |  |  | Dependency open | AI explains reports; qualified person authorizes intervention | Water journey walkthrough |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.02.04 | P10 | P10.02 Water decisions | Compare against thresholds and existing systems | Water domain lead | Not started | FALSE | Dependency open |  |  |  | P10.02.03 |  |  | Dependency open | Actual liters and effort evaluated against baseline | Water comparative results |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.03.01 | P10 | P10.03 Cross-domain accounting | Separate resource units and causal claims | Measurement lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | kg, kWh and liters never summed into invented eco-score | Metrics contract |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.03.02 | P10 | P10.03 Cross-domain accounting | Review emissions factors and boundaries | Measurement lead | Not started | FALSE | Dependency open |  |  |  | P10.03.01 |  |  | Dependency open | Food/location/time/disposal factors only if justified and versioned | Factor review |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.03.03 | P10 | P10.03 Cross-domain accounting | Measure platform compute and transport burden | Measurement lead | Not started | FALSE | Dependency open |  |  |  | P10.03.02 |  |  | Dependency open | Report available metrics and explicit unknowns; no net-zero claim | Burden register |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.03.04 | P10 | P10.03 Cross-domain accounting | Authorize next domain only with evidence | Measurement lead | Not started | FALSE | Dependency open |  |  |  | P10.03.03 |  |  | Dependency open | Actor access, measurable effect and viable operations required | Domain expansion gate |  | 6000 | J-E01 / J-W01 | Proposed work; implementation not authorized by this documentation request. | Expansion
P10.90.01 | P10 | P10.90 Phase gate | Review and accept energy and water modules discovery | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P10.01.04 | P10.02.04 | P10.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P10-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Expansion
P11.01.01 | P11 | P11.01 Federation and interoperability | Define interoperable partner capability registry | Technical lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | Permissions and availability separate from self-asserted badges | Partner API contract |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.01.02 | P11 | P11.01 Federation and interoperability | Version adapters and data sharing agreements | Technical lead | Not started | FALSE | Dependency open |  |  |  | P11.01.01 |  |  | Dependency open | Schema compatibility, consent and revocation behaviors tested | Adapter conformance report |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.01.03 | P11 | P11.01 Federation and interoperability | Add durable notifications and reconciliation | Technical lead | Not started | FALSE | Dependency open |  |  |  | P11.01.02 |  |  | Dependency open | Outbox, dedupe, retries and delivery status explicit | Delivery/replay evidence |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.01.04 | P11 | P11.01 Federation and interoperability | Verify federation without tenant leakage | Technical lead | Not started | FALSE | Dependency open |  |  |  | P11.01.03 |  |  | Dependency open | Per-offer grants, scoped projections and revocation tested | Cross-organization security report |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.02.01 | P11 | P11.02 Reliability and security | Measure load then set SLOs and capacity | Platform/security lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | P95/availability/error budgets grounded in pilot load | Capacity/SLO report |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.02.02 | P11 | P11.02 Reliability and security | Exercise backups restore and disaster recovery | Platform/security lead | Not started | FALSE | Dependency open |  |  |  | P11.02.01 |  |  | Dependency open | Recovery points/times measured with owned runbooks | Restore drill |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.02.03 | P11 | P11.02 Reliability and security | Perform abuse and data protection review | Platform/security lead | Not started | FALSE | Dependency open |  |  |  | P11.02.02 |  |  | Dependency open | Rate limits, malicious uploads, privilege abuse and retention audited | Security findings disposition |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.02.04 | P11 | P11.02 Reliability and security | Reconcile spend with outcomes and incidents | Platform/security lead | Not started | FALSE | Dependency open |  |  |  | P11.02.03 |  |  | Dependency open | Per-tenant cost limits and operational owners established | Operations dashboard evidence |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.03.01 | P11 | P11.03 Business rollout | Validate network density in one geography | Product/operations lead | Not started | FALSE | Dependency open |  |  |  | P08.90.01 |  |  | Dependency open | Match availability, acceptance and completion measured | Network cohort analysis |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.03.02 | P11 | P11.03 Business rollout | Pilot contracts pricing and support SLA | Product/operations lead | Not started | FALSE | Dependency open |  |  |  | P11.03.01 |  |  | Dependency open | Operator incentives and liability terms approved | Commercial pilot agreement |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.03.03 | P11 | P11.03 Business rollout | Gate incentives against fraud and coercion | Product/operations lead | Not started | FALSE | Dependency open |  |  |  | P11.03.02 |  |  | Dependency open | No reward for generated surplus or fabricated impact | Incentive abuse review |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.03.04 | P11 | P11.03 Business rollout | Approve phased expansion or stop | Product/operations lead | Not started | FALSE | Dependency open |  |  |  | P11.03.03 |  |  | Dependency open | Retention, trust, measured outcomes and margin support decision | Scale investment decision |  | 6000 | J-T01 / REQ-SCALE-01 | Proposed work; implementation not authorized by this documentation request. | Scale
P11.90.01 | P11 | P11.90 Phase gate | Review and accept ecosystem scale and commercial reliability | Product owner + independent reviewer | Not started | FALSE | Dependency open |  |  |  | P11.01.04 | P11.02.04 | P11.03.04 | Dependency open | All prerequisites verified; critical risks closed or explicitly rejected for rollout; human records go/revise/stop decision. | Phase gate record with reviewer, evidence links, residual risks and next scope |  | 4000 | P11-GATE | Unchecked until phase evidence is reviewed. A written plan is not implementation evidence. | Scale

## Decisions
Decisions and tradeoffs
Proposed / recommended is not human approval. Record evidence, approver and date when resolved.
Decision ID | Choice | Disposition | Recommendation | Alternatives | Reason | Owner role | Linked unit | Revisit trigger | Evidence | Approver | Decision date
DEC-PLAT-001 | First implementation lane | Proposed | One household changed-plan journey; switch to kitchen first only with better actor/data access | Three full lanes at once; generic material marketplace | Small enough to prove the shared loop; competition and residual gap still unknown | Product owner | P00.01.03 | Observed actor access and residual pain change the preferred lane
DEC-PLAT-002 | Platform expansion | Proposed | Shared trust/evidence/action core with separately gated domain modules | One universal resource engine; separate disconnected apps | Reuse coordination contracts without conflating food safety, repair and meter authority | Product owner + technical lead | P08.90.01 | Second domain cannot reuse core safely or does not show demand
DEC-PLAT-003 | Backend structure | Recommended | Modular FastAPI monolith and bounded worker when required | Microservices from day one; frontend-only logic | Fewer transaction and deployment seams while preserving domain boundaries | Technical lead | P01.90.01 | Measured scaling, security ownership or release independence justifies split
DEC-PLAT-004 | Runtime compatibility | Open | Verify current Next.js/Node support on App Hosting before pinning deployment pair | Assume repo version works; automatically downgrade | Existing package version and retrieved support schedule differ; no deploy proof | Platform lead | P01.03.01 | Official support or a measured deployed compatibility test settles pair
DEC-PLAT-005 | Canonical storage | Existing stack constraint | Firestore versioned document state and Cloud Storage media; reevaluate relational needs later | PostgreSQL now; in-memory canonical state | Fits selected stack and bounded workflows; cross-org joins need careful projections | Technical lead | P01.02.04 | Transaction contention or reporting constraints dominate
DEC-PLAT-006 | Authorization | Required invariant | Verified identity plus active membership, role, consent and resource scope; fail closed | Trust body tenant ID; default tenant; token-only organization membership | Prevent cross-tenant reads and stale authority after revocation | Security/backend lead | P01.01.04 | No relaxation; improve implementation with equivalent or stronger proof
DEC-PLAT-007 | Facts and approvals | Required invariant | Candidate isolation; explicit confirmation; immutable version-bound preview and authorized approval | Agent writes facts or self-authorizes execution | Human authority and current source state govern every physical effect | Technical lead | P03.02.04 | No relaxation; contract changes require migration and denial checks
DEC-PLAT-008 | Food policy | Required invariant | Reviewed category/site policy bundles; missing applicability holds for review | Universal hardcoded time/temperature thresholds from examples | Current local shortcuts are not established by cited rule text | Qualified policy owner | P06.01.01 | Reviewed official amendment or site policy updates versioned bundle
DEC-PLAT-009 | AI structure | Recommended | Structured extraction and one bounded allowlisted ADK coordinator, evaluated separately | Multi-agent product runtime; unlimited tool loop; rules-only forever | AI may help ambiguity; arithmetic and authority stay deterministic | AI lead | P03.03.04 | Comparison shows a step adds no benefit or a justified workflow needs more
DEC-PLAT-010 | Policy retrieval | Deferred | Small reviewed rule table and source links first | Vertex AI Search/RAG immediately | Corpus size and retrieval need are unproven; retrieved prose cannot publish policy | Policy/AI lead | P06.01.01 | Authorized corpus and real questions show retrieval improves the task
DEC-PLAT-011 | Jobs and external actions | Recommended | Outbox plus idempotent worker for durable effects; reconcile ambiguous provider states | Provider call inside transaction; blind retry after timeout | Transactions can retry and networks duplicate or hide successful effects | Backend lead | P03.02.04 | A synchronous bounded demo needs no durable external work; keep effect boundary
DEC-PLAT-012 | Product real-time behavior | Recommended | Bounded polling with versions initially; scoped events only after measured need | Persistent streams everywhere; unscoped global listeners | Recoverable and easier to secure; acknowledgement and timestamps matter first | Fullstack lead | P03.03.03 | Collaboration latency/read costs justify streams
DEC-PLAT-013 | Execution harness authority | Recommended | Google Sheet is live task status; Docs are narrative; local JSON/Markdown are dated snapshots | Dual live status in repo and Drive; autonomous two-way sync now | Native collaboration works now without product code; avoids conflicting checklists | Product/technical lead | P00.03.03 | Team needs repo-owned CI status and authorizes a synchronization tool
DEC-PLAT-014 | Measurement and incentives | Required invariant | Stage-specific physical metrics and explicit status; no unexplained eco-score or carbon credit | Automatically convert every action into CO2/water saved; reward waste volume | Prevents double counting and perverse incentives; attribution needs a counterfactual | Measurement lead | P08.03.04 | Reviewed factor methodology allows separately labeled scenarios
DEC-PLAT-015 | Partner integration and marketplace | Deferred | Simulated adapters; later permissioned local network before public marketplace | Live checkout/dispatch from advertised MCP; open marketplace immediately | Provider existence does not grant access, capacity or transaction authority | Partner lead | P06.03.04 | Rights, operational capacity, human approval and retry safeguards verified
DEC-PLAT-016 | Token and session budget | Recommended | One granular task/context packet; checkpoints and recorded actual usage | Whole corpus every turn; assume agents reduce token cost | Bounded context improves continuity; account allowance is unknown and variable | Technical lead | P00.03.02 | Observed task size/usage supports smaller or larger packet
DEC-PLAT-017 | Software factory workflow | Recommended | Role cards, task packets, two-pass review and evidence gates as documentation first | Install many overlapping skills/hooks before workflow is exercised | Deterministic enforcement should be added only for repeat failures with a measurable benefit | Technical lead | P00.03.03 | Repeated drift justifies a small approved skill or validator
DEC-PLAT-018 | API prefix and health | Proposed | One /v1 API prefix and root /health; explicitly migrate current /api/v1 client | Keep two unowned prefixes; assume health probes match | Spec and starter differ; a single documented contract prevents integration drift | Technical lead | P01.03.03 | Existing consumers require a temporary documented alias
DEC-PLAT-019 | Evaluation coverage | Recommended | Audit seed cases and add selected-lane coverage; distinguish case count from independent trials | Call 23 seeds a complete benchmark; claim all planned cases passed | Historical 23 versus 12–20/lane targets are proposals with different coverage | Evaluation lead | P02.02.04 | Risk-based coverage requires additional scenario families
DEC-PLAT-020 | Current work authorization | User constraint | Documentation/research and live planning artifacts only; implementation requires later direction | Treat this request as permission to modify application code or deploy | User explicitly requested ideation, tradeoffs and feasibility with no code changes | Product owner | P00.03.04 | User explicitly authorizes implementation scope

## Risks
Risks and next evidence
Risk ID | Risk | State | Trigger | Response / next evidence | Owner role | Linked unit | Evidence / update | Disposition
RISK-01 | Residual pain unproven | Open | Existing list/service handles chosen cases | Reconstruct real episodes and compare baseline | Product owner | P00.01.02 |  | Unresolved
RISK-02 | Data rights or authority unavailable | Open | No consenting source/decision owner | Obtain artifact rights or defer feature | Research lead | P00.02.04 |  | Unresolved
RISK-03 | Unsafe policy shortcut | Open | Unreviewed threshold or food-safety claim | Block live recovery; qualified policy review | Policy owner | P06.01.01 |  | Unresolved
RISK-04 | Deployment or model access blocked | Open | Unsupported runtime/IAM/quota | Verify early and cut optional scope | Platform lead | P01.03.01 |  | Unresolved
RISK-05 | Input burden exceeds benefit | Open | Corrections take longer than baseline | Measure all actor effort; redesign capture | Product lead | P08.01.03 |  | Unresolved
RISK-06 | AI adds no incremental value | Open | No better correctness/effort net of cost | Keep rules; remove unnecessary model step | AI/evaluation lead | P03.03.04 |  | Unresolved
RISK-07 | Physical logistics dominates | Open | No safe capacity or processing destination | Audit failures; a directory cannot create capacity | Partner lead | P06.02.02 |  | Unresolved
RISK-08 | Impact overclaim/double counting | Open | Simulation shown as measured saving | Separate stage, origin, verification and attribution | Measurement lead | P08.03.04 |  | Unresolved
RISK-09 | Economics or payer unproven | Open | Support exceeds payer value | Measure costs and real pricing response | Product owner | P08.02.04 |  | Unresolved
RISK-10 | Context drift/false completion | Open | Missing evidence or duplicate live status | Stable IDs, gates and session handoff | Technical lead | P00.03.03 |  | Unresolved

## Sessions
Session handoffs
Session ID | Date (IST) | Scope | Units / artifacts | Evidence | Result | Open blocker | Next unit | Decisions | Usage note
S-2026-10-15-01 | 2026-10-15 | Research and documentation only | 42 sources; blueprint + 156-unit plan | Control room/source register | Documentation prepared; implementation unverified | Human review, access and scope decisions pending | P00.01.01 | DEC-PLAT-001–020 as labeled | Actual account budget unknown; bounded task packets

## Guide
How to keep this harness current
Topic | Operating rule
Authority | Tasks is live status; Docs are narrative; local files are snapshots.
Completion | Set Complete + Done + evidence + reviewer + updated date. Dependencies must be Verified.
Formula limit | Use filters, not physical sorting. Dependencies must point to earlier unique IDs; missing/later IDs fail closed.
Adding work | Append unique IDs after prerequisites, copy formulas/validation, extend bounded ranges and update phase gates.
No background sync | No repository monitor, CI integration, agent scheduler or two-way Drive sync is implemented.
Ownership | Initial owners are roles. Assign actual people/agents before execution.
Token allowance | 6,000 context tokens/unit is a planning input; actual output/tool/delegation usage varies.
Evidence quality | Formulas check presence/state, not truth, safety qualification or link accessibility.
Scope | Documentation only. Later code, deployment and physical effects require relevant direction.
Review | Critical auth/safety/data-loss review first, then maintainability, UX and missing checks.
Recovery | Back up before structural changes; preserve IDs, revisions, failed output and decisions.
Source folder | https://drive.google.com/drive/folders/1iTwjBm5FrwthFEzuTZ91D33sRSB4ft9v